Vancel Technologies Pvt. Ltd.

Enterprise Travel, Approval Workflow & Expense Management Platform

Zoho-Native Solution Proposal

| Prepared For | Prepared By |
| --- | --- |
| Kaushik Kumar | Vetri Murugan, Chief Solutions Architect Vancel Technologies Pvt. Ltd. |
| India-based enterprise client | contact@vanceltech.com ¦ www.vanceltech.com |
| Date: May 2026 | Version: 2.0 ¦ Confidential |

Proposal Purpose This document presents a professional services proposal for designing, implementing, integrating, and deploying a Zoho-native enterprise Travel Request, Approval Workflow, and Expense Management Platform for an organization of up to 10,000 employees.

Important: All phone numbers from the earlier draft have been removed. Vancel contact details are limited to official email and website references in this version.

# Contents

Executive Summary

Understanding of Client Requirements

Recommended Zoho-Native Solution

Scope of Services by Vancel

Information to be Provided by Vancel

Client Inputs Required

Implementation Methodology and Timeline

Commercial Proposal

Technical and Security Standards

Assumptions, Exclusions, and Next Steps

# 1. Executive Summary

Vancel Technologies proposes to design and implement an enterprise-grade Travel Request, Approval Workflow, and Expense Management Platform using a Zoho-native hybrid architecture. The solution is intended to digitize the complete corporate travel lifecycle, from travel request initiation to approvals, ticketing coordination, expense submission, receipt processing, reimbursement tracking, and executive reporting.

Commercial Summary One-time professional services fee: INR 18,00,000 plus applicable GST. Estimated annual Zoho licensing: INR 12,44,000 to INR 15,94,000, subject to final user counts and Zoho enterprise pricing confirmation.

The architecture is designed to avoid blanket licensing for all employees. Only core operations users require Zoho Creator access, while the broader employee population uses Zoho Expense on an active-user basis where billing depends on actual monthly expense submitters.

# 2. Understanding of Client Requirements

Based on the initial requirement context, the client requires a unified digital platform covering four operating domains:

| Requirement Area | Business Need |
| --- | --- |
| Air Ticketing Management | Domestic and international travel requests; one-way, round-trip, and multi-city itineraries; traveler profiles; vendor coordination; PNR and e-ticket tracking; cancellation and rescheduling workflows. |
| Approval Workflow Management | Configurable multi-level approvals by department, amount, destination type, employee grade, delegation rules, escalations, mobile approvals, and complete audit trail. |
| Expense Management | Expense submission, OCR-based receipt capture, per diem rules, multi-currency, policy validation, GST/tax support, advances, settlements, duplicate detection, and reimbursement status tracking. |
| Reporting and Integration | MIS dashboards, travel spend analytics, approval aging, vendor-wise spend, budget versus actual tracking, HRMS/AD sync, Finance/ERP integration, email notifications, and optional travel API connectivity. |

# 3. Recommended Zoho-Native Solution

The recommended architecture uses Zoho Creator for the custom travel desk application, Zoho Expense for claim and reimbursement workflows, Zoho Analytics for MIS reporting, and Zoho Flow as the integration and automation layer. This approach keeps the platform SaaS-hosted, scalable, and faster to deploy than a fully custom application.

## 3.1 Core Module Stack

| Zoho Module | Role | Key Capabilities |
| --- | --- | --- |
| Zoho Creator | Custom Air Ticketing Module and Travel Desk portal | Travel request forms, PNR management, vendor mapping, e-ticket storage, reschedule/cancellation workflows, admin dashboard. |
| Zoho Expense | Expense submission and reimbursement management | OCR receipt scanning, per diem, multi-currency, GST/tax rules, policy enforcement, mobile app, duplicate detection. |
| Zoho Analytics | MIS dashboards and executive reporting | Travel spend, approval aging, vendor-wise reports, budget versus actual, custom report builder. |
| Zoho Flow | Integration and automation orchestration | HRMS sync, ERP bridges, email/SMS/WhatsApp triggers, approval routing webhooks, third-party API connectors. |
| Zoho CRM / Zoho Sign | Optional vendor and compliance extensions | Vendor registry, agency contact management, SLA tracking, high-value approval signing, audit trail. |

## 3.2 Integration Architecture

| External System | Integration Route | Purpose |
| --- | --- | --- |
| HRMS / Active Directory | Zoho People API or Zoho Flow | Employee master sync, department hierarchy, manager mapping, SSO readiness. |
| Finance / ERP Systems | Zoho Flow API bridge | Budget checks, GL code allocation, journal entry handoff, reimbursement status updates. |
| Email / Collaboration | Zoho Mail/Cliq or client email tools | Approval notifications, escalations, travel desk alerts, exception communication. |
| Travel Vendor APIs | Zoho Creator + Zoho Flow | Fare comparison, PNR sync, agency booking updates, optional GDS or corporate booking tool integration. |
| Payment / Settlement Systems | Zoho Expense + finance integration | Advance settlement, reimbursement processing, vendor payout workflow support. |

Integration Clarification Zoho modules listed as integration routes are not automatically mandatory licenses. If the client already uses SAP, Oracle, Tally, Outlook, Microsoft Teams, Okta, or other non-Zoho tools, Vancel will connect to those systems through available APIs, SFTP feeds, webhooks, or agreed integration methods.

# 4. Scope of Services by Vancel

Vancel will be responsible for solution design, Zoho configuration, custom module development, integration engineering, testing coordination, deployment support, and structured knowledge transfer. The service scope is summarized below.

| Service Area | Vancel Responsibility |
| --- | --- |
| Discovery and Design | Requirement workshops, current process review, approval matrix design, policy rule mapping, integration assessment, and Solution Design Document. |
| Zoho Creator Build | Custom travel request forms, itinerary capture, PNR and ticket tracking, vendor mapping, Travel Desk dashboard, cancellation/rescheduling workflows. |
| Zoho Expense Configuration | Expense categories, per diem rules, OCR configuration, multi-currency setup, policy compliance, advance and reimbursement workflows. |
| Workflow and Automation | Dynamic approval routing, conditional logic, delegation of authority, escalation handling, email/mobile approval triggers, audit trail configuration. |
| Integration Delivery | HRMS/AD sync, Finance/ERP connectors, travel vendor API bridges where available, notification workflows, data exchange validation. |
| Analytics and Reporting | Executive dashboards, spend analytics, approval aging, vendor-wise reports, budget versus actual views, export-ready report templates. |
| Testing, Training, Go-Live | SIT support, UAT coordination, admin training, end-user orientation, production rollout, and hypercare support. |

# 5. Information to be Provided by Vancel

Service Provider Disclosure Requirement The following information should be formally provided by Vancel to the client before contract execution or during Phase 1. This makes the engagement auditable, procurement-ready, and aligned with enterprise vendor governance expectations.

| Information Category | Details to be Furnished by Vancel |
| --- | --- |
| Corporate and Legal Details | Registered company name, registered office address, CIN/GSTIN/PAN, authorized signatory details, bank account information for invoicing, and standard legal notices. |
| Commercial Documents | Detailed Statement of Work, tax-compliant quotation, payment milestone schedule, AMC options, assumptions, exclusions, change request process, and proposal validity period. |
| Project Governance | Named project manager, solution architect, escalation matrix, communication cadence, meeting rhythm, weekly status report format, RAID log template, and acceptance sign-off process. |
| Solution Design Artifacts | Solution Design Document, workflow diagrams, role/permission matrix, Zoho module configuration map, integration architecture, data flow diagram, and test strategy. |
| Security and Compliance Inputs | Access control approach, data handling practices, audit trail design, credential management approach, backup/recovery reliance on Zoho, and security responsibilities shared between Vancel, Zoho, and client IT. |
| Delivery Evidence | Milestone deliverables, demo recordings or walkthroughs where agreed, UAT issue tracker, training materials, admin handover notes, and go-live readiness checklist. |
| Post-Go-Live Support | Hypercare duration, support scope, SLA categories, issue reporting process, AMC coverage, enhancement request workflow, and transition-to-support checklist. |

# 6. Client Inputs Required

The following inputs are required from the client to finalize scope, licensing, integrations, and delivery schedule. Delays in these inputs may affect project timelines and commercial assumptions.

| Input Area | Client Information Required |
| --- | --- |
| User and Role Scope | Total employee count, expected monthly expense submitters, Travel Desk users, finance users, approving manager count, department hierarchy, grade structure. |
| Policies and Approval Rules | Travel policy, expense policy, per diem rules, grade-wise entitlements, domestic/international approval rules, escalation rules, delegation rules. |
| Systems and Integration Access | HRMS details, Finance/ERP details, SSO/AD details, API documentation, sandbox credentials, SFTP/API availability, security approvals. |
| Data and Migration | Employee master data, vendor/travel agency master data, historical travel or expense data if migration is required, data retention expectations. |
| Commercial and Timeline Inputs | Preferred go-live date, rollout approach, existing Zoho subscriptions, procurement process, invoice details, acceptance and payment contacts. |

# 7. License Optimization Strategy

For a 10,000-employee organization, the key cost-control principle is targeted procurement rather than blanket licensing. Zoho Creator should be licensed only for core system administrators, Travel Desk operators, and finance operations users. The broader employee base should use Zoho Expense under the active-user model.

| Role Category | Users | Product | License Type | Rationale |
| --- | --- | --- | --- | --- |
| System Admin / Workflow Owner | 3-8 | Zoho Creator Plus | Full named user | Platform control, policy configuration, audit access. |
| Travel Desk Operations | 10-25 | Zoho Creator Plus | Full named user | PNR updates, vendor booking, e-ticket management. |
| Finance / Reimbursement Ops | 5-15 | Zoho Creator Plus + Expense | Named operational user | Expense approval, settlement, GST processing. |
| Reporting Manager / Approver | 100-300 | Zoho Expense | Approval-only unless claim submitted | Charged only if also submitting expense reports. |
| Employee / Traveler | Up to 10,000 | Zoho Expense | Active-user monthly billing | Only monthly claim submitters are billed. |

Procurement Recommendation Use Zoho Creator Plus for approximately 20-40 core operations/admin users and Zoho Expense Premium for the general employee base. Zoho One is not recommended for this use case because all-employee pricing would likely be commercially inefficient for a 10,000-employee population.

# 8. Implementation Methodology and Timeline

| Phase | Timeline | Scope | Key Deliverable |
| --- | --- | --- | --- |
| Phase 1: Discovery & Solution Design | Weeks 1-3 | Workshops, approval matrix validation, policy mapping, module configuration design, integration specification. | Signed-off Solution Design Document. |
| Phase 2: Core Build | Weeks 4-12 | Zoho Creator travel module, Zoho Expense configuration, approval engine, workflow automation. | Working system in staging environment. |
| Phase 3: Integration & Testing | Weeks 13-18 | HRMS/AD, Finance/ERP, travel API connections, dashboards, SIT, performance and security review. | Integrated system ready for UAT. |
| Phase 4: UAT, Training & Go-Live | Weeks 19-24 | UAT support, issue closure, administrator training, end-user orientation, phased production rollout. | Live production system with go-live sign-off. |

# 9. Commercial Proposal

## 9.1 One-Time Professional Services Fee

| Delivery Component | Scope | Cost |
| --- | --- | --- |
| Discovery & Architecture | Requirements workshops, workflow mapping, approval matrix design, SDD documentation. | INR 2,50,000 |
| Zoho Creator Travel Module Build | Travel request forms, multi-city handling, PNR, vendor mapping, cancellation/reschedule, Travel Desk dashboard. | INR 6,50,000 |
| Zoho Expense Configuration | Expense policies, per diems, multi-currency, OCR rules, policy compliance, reimbursements, advances. | INR 3,50,000 |
| Integration via Zoho Flow | HRMS/AD sync, ERP connections, email/SMS/WhatsApp alerts, approval triggers, travel API bridges. | INR 2,50,000 |
| Analytics & MIS Dashboards | Travel spend, approval aging, vendor-wise, budget versus actual reports, export capabilities. | INR 1,50,000 |
| QA, UAT, Training & Go-Live | Testing, UAT coordination, administrator and user training, phased deployment, hypercare. | INR 1,50,000 |
| Total Professional Services | One-time implementation fee before tax. | INR 18,00,000 |
| GST at 18% | Applicable statutory tax. | INR 3,24,000 |
| Total Payable Including GST | Professional services total including GST. | INR 21,24,000 |

## 9.2 Estimated Annual Zoho Licensing

| License Component | Basis | Estimated Annual Cost |
| --- | --- | --- |
| Zoho Creator Plus Bundle | ~25 named users covering Creator, Flow, and Analytics. | INR 3,00,000 - INR 5,00,000 |
| Zoho Expense Premium | ~500 monthly active submitters at estimated INR 149/user/month. | INR 8,94,000 |
| Additional Zoho Modules | Zoho Sign, Zoho CRM, or other extensions if confirmed in scope. | INR 50,000 - INR 2,00,000 |
| Total Estimated Annual Licensing | Planning estimate only; final quote to be confirmed by Zoho. | INR 12,44,000 - INR 15,94,000 |

Licensing Note Zoho licensing should be purchased directly by the client from Zoho Corporation and invoiced separately from Vancel professional services. Final pricing depends on actual user counts, selected editions, enterprise discounts, and Zoho commercial terms at procurement time.

## 9.3 Annual Maintenance Contract Options

| AMC Tier | Coverage | Annual Cost |
| --- | --- | --- |
| Standard | Bug fixes, L2 support, monthly check-ins. | INR 1,50,000 per annum |
| Enhanced (Recommended) | Standard coverage plus minor enhancements, workflow updates, and new report builds. | INR 3,00,000 per annum |
| Premium | Enhanced coverage plus dedicated account manager, priority SLA, and quarterly business review. | INR 5,00,000 per annum |

## 9.4 Total Cost of Ownership Summary

| Cost Layer | Amount |
| --- | --- |
| One-time implementation including GST | INR 21,24,000 |
| Zoho licensing estimated midpoint | INR 14,00,000 |
| AMC - Enhanced tier | INR 3,00,000 |
| Estimated Year 1 Total | INR 38,24,000 |
| From Year 2 onwards | INR 17,00,000 per annum |

# 10. Technical and Security Standards

Data encryption through TLS in transit and AES-256 at rest, managed within Zoho SaaS controls.

Role-based access control with granular field-level and record-level permissions.

System-generated audit trails for requests, approvals, edits, reimbursements, and administrative actions.

Support for SOC 2 Type II, ISO 27001, GDPR-ready handling, and enterprise audit requirements subject to Zoho platform controls.

Native mobile support through Zoho Expense for iOS and Android, with web access for administrative workflows.

REST API and OAuth 2.0 based integration availability, subject to client system readiness.

Zoho-managed backup, recovery, disaster recovery, and auto-scaling infrastructure.

# 11. Assumptions and Exclusions

Client will provide timely access to business stakeholders, technical contacts, policy documents, and integration documentation.

API availability, sandbox access, and third-party vendor cooperation are prerequisites for integration delivery.

Major custom features outside the stated scope will be handled through a mutually approved change request.

Zoho subscription costs, third-party API fees, SMS/WhatsApp gateway charges, and payment gateway charges are excluded from Vancel professional services unless expressly included in the final SOW.

Data migration scope is limited to the data sets confirmed during Phase 1. Historical migration beyond agreed templates may require additional effort.

The proposed timeline assumes prompt client review and sign-off at each milestone.

# 12. Pre-Engagement Clarification Questions

What is the total number of employees expected to use the travel request module in the first year?

How many employees are likely to submit expense claims per month on average?

How many Travel Desk and finance operations users will require administrative access?

How many approval levels exist, and do they vary by department, cost center, grade, or geography?

Which HRMS, Finance/ERP, SSO/AD, email, and collaboration systems are currently used?

Are APIs, SFTP feeds, webhooks, or sandbox environments available for those systems?

Are travel and expense policies formally documented and approved?

Are GST input tax credit, TDS, statutory audit, or external auditor access requirements applicable?

Is historical travel and expense data migration required?

Is there a fixed go-live deadline or preferred phased rollout sequence?

Does the client already hold any Zoho subscriptions that should be reused or integrated?

# 13. Why Vancel Technologies

Vancel Technologies is positioned as a solutions engineering partner focused on practical enterprise systems, responsible AI-assisted development, and workflow-led digital transformation. For this engagement, Vancel brings Zoho ecosystem architecture capability across Creator, Expense, Flow, Analytics, and CRM, combined with enterprise approval workflow engineering and India-specific operational understanding around GST, statutory audit readiness, and data governance expectations.

The engagement will be delivered through milestone-based governance. Each project phase concludes with a tangible client-reviewed deliverable before the next phase begins, ensuring transparency, control, and commercial alignment throughout the implementation lifecycle.

# 14. Recommended Next Steps

Schedule a 60-minute discovery workshop with Travel, Finance, HR, IT, and procurement stakeholders.

Confirm user count assumptions for Zoho Creator and Zoho Expense licensing.

Share current travel policy, expense policy, approval matrix, HRMS details, Finance/ERP details, and SSO requirements.

Finalize and sign the Master Services Agreement and Phase 1 Statement of Work.

Initiate Zoho trial or sandbox access for Zoho Creator and Zoho Expense for early stakeholder validation.

# Confidentiality Notice

This proposal is confidential and prepared exclusively for the named recipient. It may not be shared, reproduced, or distributed without prior written consent from Vancel Technologies Pvt. Ltd.